## Slide 1
Implementation Plan April 2025 – March 2028
Phase 1: April 2025 – March 2026
New EHCPs - Funding takes effect immediately when the EHCP is finalised from April 25
KST 2025 where a pupil changes setting – Funding notified from April 25 takes effect from September 25
Mainstream and Special target cohorts transferred at annual review - Funding takes effect from April 2026 for m/s or September 2026 academy. Current rates held
Phase 1: Total EHCPs transferred 507
Phase 2: April 2026 – March 2027
KST 2025 where a pupil changes setting – Funding notified from April 26 takes effect from September 26
Mainstream Target cohorts transferred at annual review - Funding takes effect from date of finalised plan – current rates held (gains and losses)
Special target cohorts transferred at annual review Funding takes effect from September 2027 (academy FY) current rates held
Phase 2: Total EHCPs transferred 507
Phase 3: April 2027 – March 2028
KST 2025 where a pupil changes setting – Funding notified from April 27 takes effect from September 27
Mainstream target cohorts transferred at annual review - Funding takes effect on finalised plan – current rates held (gains and losses)
Phase 3: Total EHCPs transferred 133

## Slide 2
Implementation Proposed Detailed Schedule/Timeline
Mainstream and Resource Base Scheule
Special School Schedule
Phase 1: April 25-March 26 |  |  | Phase 2: April 26 -March 27 |  |  |  | Phase 3: April 27 - March 28 |  | 
NCY April 25* | Total EHCP |  | NCY April 25 | NCY April 26 | Total EHCP |  | NCY April 25 | NCY April 27 | Total EHCP
Y-1 | 19 |  | Y-2 | Y-1 | 4 |  | R | Y2 | 54
Y2 | 76 |  | Y1 | Y2 | 67 |  | Y4 | Y6 | 79
Y3 | 67 |  | Y5 | Y6 | 83 |  |  |  | 
Y6 | 82 |  | Y8 | Y9 | 57 |  |  |  | 
Y9 | 74 |  | Y7 | Y8 | 73 |  |  |  | 
Y11** | 63 |  | Y10 | Y11** | 65 |  |  |  | 
Total | 381 |  | Total |  | 349 |  | Total |  | 133
April 25-March 26 |  |  | April 26-March 27 |  |  |  |  |  | 
NCY April 25 | Total EHCP |  | NCY April 25 | NCY April 26 | Total EHCP |  |  |  | 
R | 9 |  | Y1 | Y2 | 24 |  |  |  | 
Y2 | 25 |  | Y4 | Y5 | 23 |  |  |  | 
Y3 | 20 |  | Y5 | Y6 | 17 |  |  |  | 
Y6 | 21 |  | Y8 | Y9 | 29 |  |  |  | 
Y9 | 27 |  | Y7 | Y8 | 32 |  |  |  | 
Y11** | 24 |  | Y10 | Y11** | 33 |  |  |  | 
Total | 126 |  | Total |  | 158 |  |  |  | 
*Please note the NCY in this table reflects year group as at April 25 and in the corresponding adjusted year group in each implementation phase. Schools should note that year group changes in September are not shown in this table and you should be mindful of this in planning annual review and banding changes.
** Pupils remaining in 6th form (mainstream or special school only

## Slide 3
Implementation Plan – System Arrangements
Moderation Plan
Programme of internal Moderation built in to process
Quality Assurance
Audit tool rolled out for EHCPs and Annual Reviews
Monitoring, Review and Evaluation
Briefing at Secondary Heads, Primary Heads and Wokingham Education Partnership and SENDCO Network in May/June 2025
Communication
Specialist training for Team Manager, Senior Case Manager and Area SENDCO which includes:
Online training modules
Bespoke EBT workshop
Regular and ongoing moderation
Progress against plan monitored
Actuals vs projection monitored and modelling updated
Imosphere ongoing analysis and support
Annual whole system evaluation
Annual peer moderation – linked to other mechanisms
Annual review guidance reviewed and rolled out
Drop in briefing sessions for SENDCOs and Headteachers September 2025 and April 2026
SENDCO newsletter, Schools Weekly email and SENDCO Hub website
Briefing for SEND Voices
Parent news letter and local offer website
Reporting to Schools Forum, Transformation Board and CLT
Training